CIS 481 – Intro to Information Security

CLASS EXERCISE # 10

Grading ID: N7149

Problem 1

Name and describe the four basic conversion strategies discussed in the text that may be used when converting to a new system. Under which circumstances would each be considered the right approach? (10 pts.)

Direct changeover: involves stopping the old system and starting the new one without any overlap.

Parallel operations: Involves running the new system concurrently with the old system.

Phased implementation: Involves a measured rollout of the planned system; only part of the system is brought out and disseminated across an organization before the next piece is implemented.

Pilot implementation: Involves implementing the entire system into a single office, department, or division, and dealing with issues that arise before expanding to the rest of the organization.

Direct changeover could be considered the right approach when requiring employees to use a new password with a stronger degree of authentication on a specific date or telling the company to change procedures when an old firewall and shut down and the new one is turned on.

Phased implementation is usually the best approach when it comes to security project implementation. For instance, when an organization seeks to upgrade both its VPN and IDPS systems, it may introduce the new VPN solution that employees can use to connect to the organizations network while they’re traveling.

Pilot implementation is usually the best approach when an isolated group can serve as a test subject which prevents any problems with the new system from dramatically interfering with the performance of the organization as a whole.

Parallel operations are usually the best approach by reinforcing an organization’s information security by allowing the old system to serve as a backup for the new systems if they fail or are compromised.

Problem 2

Complete Exercise 1 from p. 576 of the text. Model your WBS on Table 10-1 from p. 541 of the text. Assume that work on the project may begin as early as next Monday. (15 pts.)

| Task or Subtask | Resources | Start (S) & End (E) Dates | Estimated Effort in Hours | Estimated Capital Expense | Estimated Noncapital Expense | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| 1 Contact network engineering team to ensure hardware is compatible with network | Network Architect | S: 6/24 E: 6/26 | 2 | $0 | $200 |  |
| 2 Purchase Web Filter | Network Architect and Purchasing Group |  |  |  |  |  |
| 2.1 Order Web Filter Through Purchasing Group | Network Architect | S: 6/27 E: 6/27 | 1 | $0 | $0 | 1 |
| 2.2 Order Web Filter from Manufacturer | Purchasing Group | S: 6/28 E: 6/28 | 2 | $1800 | $0 | 2.1 |
| 2.3 Web Filter Delivered | Purchasing Group | E: 7/19 | 1 | $0 | $0 | 2.2 |
| 3 Purchase Technical Support Contract | Purchasing Group | S: 6/28 E: 6/28 | 1 | $3,240 | $0 | 1 |
| 4 Purchase Additional Software Components | Purchasing Group | S: 6/28 E: 6/28 | 1 | $550 | $0 | 1 |
| 5 Submit Change Request to Implement Hardware | Change Control Board | S: 7/19 E: 8/5 | 1 | $0 | $0 | 2 |
| 6 Administrator Attends Training on New Hardware Device | Training Department and Administrator | S: 8/5 E: 8/9 | 40 | $0 | $0 | 3 |
| 7 Installation and Configuration of Hardware and Software Components | Contracted Vendors | S: 8/5 E: 8/18 | 150 | $0 | $21,000 | 2, 4 |

| Task or Subtask | Resources | Start & End Dates | Estimated Effort in Hours | Estimated Capital Expense | Estimated Noncapital Expense | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| 1 Ongoing Administrative Functions | Administrator | Ongoing | 4 per week | $0 | $0 |  |
| 2 Monthly Subscription | Administrator and Purchasing Group | Ongoing |  | $250 per month | $0 |  |